## Roadmap Tracker
Citizen AI Engineer Program — Roadmap Tracker
Track implementation progress across all phases. Update Status and Date Completed as tasks are finished.
Phase | Task # | Task | Description | Owner | Status | Date Completed | Notes
Phase 0 — Get the Foundation Approved
Phase 0 | 0.1 | CIO decision: Enterprise vs Teams plan | Evaluate the compliance and cost analysis. Make the go/no-go decision on Claude Enterprise vs Teams. This gates all subsequent phases. |  | Not Started
Phase 0 | 0.2 | Enterprise procurement | Purchase Claude Enterprise (minimum 20 seats). Options: self-serve at anthropic.com, sales-assisted, or AWS Marketplace. |  | Not Started
Phase 0 | 0.3 | Draft Acceptable Use Policy (AUP) | Legal/InfoSec drafts the AI AUP covering Driving Zones, data classification, No-Drive prohibitions, enforcement, and signed acknowledgment requirement. |  | Not Started
Phase 0 | 0.4 | Update Information Security Policy | Amend the existing InfoSec policy to include AI tools, referencing the Driving Zones model and the AUP. |  | Not Started
Phase 0 | 0.5 | Brief Board of Directors | Present the Citizen AI Engineer initiative to the Board: scope, compliance posture, governance model, and rollout plan. |  | Not Started
Phase 1 — Build the Guardrails
Phase 1 | 1.1 | Deploy managed-settings.json + managed-mcp.json | Configure and push org-wide managed settings via the Claude Enterprise admin console. Sets permission rules, sandbox enforcement, and MCP deny-by-default. |  | Not Started
Phase 1 | 1.2 | Write company-wide CLAUDE.md template | Author the global CLAUDE.md: Jira-first rule, no credentials policy, Zone rules, approved tool list, and escalation instructions. |  | Not Started
Phase 1 | 1.3 | Configure PreToolUse blocking hooks | Write and deploy hooks that block dangerous commands before execution: rm -rf, push to main, secret/credential string patterns. |  | Not Started
Phase 1 | 1.4 | Configure PostToolUse audit hooks | Write and deploy hooks that log all tool use to the SIEM via the Compliance API. Every Claude action leaves an audit trail. |  | Not Started
Phase 1 | 1.5 | Set up SCIM provisioning | Configure SCIM between the identity provider and Claude Enterprise. Automates onboarding/offboarding. Directly remediates SOC2 audit exceptions CC5.1.1 and CC6.1.2. |  | Not Started
Phase 1 | 1.6 | Verify audit log pipeline | Confirm audit logs are flowing correctly from Claude Enterprise to the SIEM. Spot-check a sample of events. Sign off before rollout. |  | Not Started
Phase 2 — Build the Certification Program
Phase 2 | 2.1 | Make course strategy decision (Option A / B / C) | Decide: Anthropic Academy only (A), internal only (B), or hybrid (C). Recommended: hybrid — Academy for Module 1 fundamentals, internal for Modules 2 and 3. |  | Not Started
Phase 2 | 2.2 | Audit Anthropic Academy catalog | Review current Anthropic Academy course offerings. Designate specific courses for Module 1 (AI Fundamentals). Confirm availability and certificate/proof-of-completion mechanism. |  | Not Started
Phase 2 | 2.3 | Build Module 2 — Responsible Use at iAltA | Develop the internal course covering: Driving Zones in full (Zones 1–3 + No-Drive), AUP walkthrough, data classification framework, real iAltA scenarios and edge cases. |  | Not Started
Phase 2 | 2.4 | Build Module 3 — Advanced Workflows | Develop the internal course covering: approved MCP servers and their Zone 3 implications, agentic task design, Jira-first enforcement, CLAUDE.md awareness, hands-on Zone 3 exercise. |  | Not Started
Phase 2 | 2.5 | Build assessments and quizzes | Write a quiz for each module and a final assessment. Employees must pass the full assessment to receive their license. |  | Not Started
Phase 2 | 2.6 | Create completion tracker and intake process | Set up the central certification tracker (HubSpot form, Google Sheet, or equivalent). Define the intake process: submission → review → certification record confirmed → access provisioned. |  | Not Started
Phase 2 | 2.7 | Design the license record | Create the template for the signed, dated completion document issued to each employee upon certification. This is the official record of their license. |  | Not Started
Phase 3 — Company-Wide Rollout
Phase 3 | 3.1 | Confirm all employees complete full certification | Verify that every employee has completed all three modules, passed the assessment, and signed the AUP before any Claude access is provisioned. No exceptions. |  | Not Started
Phase 3 | 3.2 | Configure and test SCIM-based provisioning | Run end-to-end test of the SCIM provisioning flow: certification confirmed → access granted. Test deprovisioning on a test account. |  | Not Started
Phase 3 | 3.3 | Company-wide announcement (all-hands) | Announce the program is live. Communicate that using AI without a license is a policy violation. Provide instructions for starting certification. |  | Not Started
Phase 3 | 3.4 | Certification tracker live and maintained | Confirm the central tracker is operational and being actively maintained. All completions are logged. Access control cross-references the tracker. |  | Not Started
Phase 4 — Steady State
Phase 4 | 4.1 | Select ongoing engagement model | CIO selects the engagement model for ongoing program management: Option 1 (1-on-1 quarterly), Option 2 (weekly office hours), Option 3 (monthly mandatory group), Option 4 (tiered by usage), or Option 5 (async-first). |  | Not Started
Phase 4 | 4.2 | [Annual] AUP re-certification | All employees re-read the AUP and re-sign annually. Update the certification tracker with renewal dates. |  | Not Started
Phase 4 | 4.3 | [Annual] Vendor compliance review | Obtain and review the updated Anthropic SOC2 Type II report. Confirm no new compliance gaps. Document findings. |  | Not Started
Phase 4 | 4.4 | [Annual] Curriculum review | Audit all three course modules for accuracy and relevance. Update content for new Claude capabilities, policy changes, new approved MCP servers, and any zone clarifications. |  | Not Started
Phase 4 | 4.5 | [Annual] Risk assessment update | Update the organizational AI risk assessment to reflect current usage patterns, incidents, and any changes to the threat landscape or compliance requirements. |  | Not Started
Phase 4 | 4.6 | [Annual] Incident response drill | Run a tabletop exercise with an AI-specific scenario (e.g., a Zone 3 violation, a credential leak via Claude, or an agentic task that exceeded scope). Document lessons learned. |  | Not Started

## Legend & Instructions
How to Use This Tracker
COLUMN | DESCRIPTION
Phase | Which phase of the roadmap this task belongs to.
Task # | Unique identifier for cross-referencing with the roadmap document.
Task | Short name for the task.
Description | Full context for what needs to be done and why.
Owner | The person responsible for completing this task. Fill in as assignments are made.
Status | Select from the dropdown: Not Started / In Progress / Complete / Blocked / N/A
Date Completed | Enter the date when the task reaches Complete status (format: MM/DD/YYYY).
Notes | Any context, blockers, decisions made, or links to supporting documents.
STATUS COLORS
Not Started | Task has not been started yet (default).
In Progress | Task is actively being worked on.
Complete | Task is finished and verified.
Blocked | Task cannot proceed — note the blocker in the Notes column.
N/A | Task is not applicable given decisions made (e.g., task for Option A if Option C was chosen).