# Citizen AI Engineer Program

Implementation Roadmap

───────────────────────────────────────────────────────────────────────────────────────────────

## Program Overview

The Citizen AI Engineer initiative empowers every non-technical employee at iAltA to use Claude AI safely, productively, and in full compliance with our SOC2 Type II and ISO 27001 certifications. Employees receive a single AI license upon completing a comprehensive certification program and signing the Acceptable Use Policy. The license grants full access to Claude, including MCP servers and agentic workflows. Governance is handled by the Driving Zones framework, which categorizes work by data sensitivity and enforces appropriate process requirements at the system level — not by restricting which tools employees can access.

## The Driving Zones Model

Every task falls into one of four zones determined by the data involved, not the tool used.

| Zone | Data Involved | Process Required |
| --- | --- | --- |
| Zone 1 — Private Property | Public data only. No company information. | None — just use Claude. |
| Zone 2 — Residential | Internal, non-confidential. No PII or client data. | GitHub repo + branch protection + code review. |
| Zone 3 — Highway | Confidential, PII, client data, MCP servers, production systems. | Zone 2 requirements + Jira ticket + approved MCP servers + audit logging + manager review. |
| No-Drive Zone | Credentials, secrets, bypassing guardrails, unapproved tools. | Prohibited always. Violation = license revocation. |

Override rule: Any MCP server connecting to a live system automatically triggers Zone 3, regardless of the data involved.

───────────────────────────────────────────────────────────────────────────────────────────────

PHASE 0  —  GET THE FOUNDATION APPROVED

All subsequent phases depend on the decisions made here. Nothing is built until the plan is approved and the infrastructure decision is made.

CIO decision on Enterprise vs Teams plan

Enterprise procurement (minimum 20 seats; self-serve at anthropic.com or sales-assisted)

Legal/InfoSec drafts the Acceptable Use Policy (AUP)

Update the Information Security Policy to include AI tools

Brief Board of Directors

───────────────────────────────────────────────────────────────────────────────────────────────

PHASE 1  —  BUILD THE GUARDRAILS

Technical controls are deployed centrally and cannot be overridden by individual users. These must be in place before any employee accesses Claude.

Deploy managed-settings.json + managed-mcp.json via enterprise admin console

Write company-wide CLAUDE.md template (Jira-first, no credentials, Zone rules baked in)

Configure PreToolUse blocking hooks (block: rm -rf, push to main, secret/credential patterns)

Configure PostToolUse audit hooks (log all tool use to SIEM via Compliance API)

Set up SCIM provisioning — directly remediates SOC2 audit exceptions CC5.1.1 and CC6.1.2

Verify audit log pipeline is flowing correctly to security tooling

───────────────────────────────────────────────────────────────────────────────────────────────

PHASE 2  —  BUILD THE CERTIFICATION PROGRAM

The certification program is the gateway to Claude access. Every employee completes the full curriculum — all three modules — before receiving a license. There are no partial licenses or tiered access levels. Think of it as a driver's license: you either have it or you don't, but earning it requires demonstrating knowledge of all roads.

## Course Strategy Decision

Before building, the program lead must decide on the delivery model:

| Option | Approach | Trade-offs |
| --- | --- | --- |
| A — Anthropic Academy Only | Use free Anthropic Academy courses as the curriculum backbone. Employees submit proof of completion. | Low build cost. Dependent on Anthropic's catalog staying current and available. |
| B — Internal Only | Build all course content in-house using Claude. Full control over content and tone. | Higher upfront effort. You own and maintain everything indefinitely. |
| C — Hybrid (Recommended) | Anthropic Academy covers AI fundamentals. Internal courses cover iAltA-specific rules, Driving Zones, workflows, and hands-on exercises. | Best balance of build effort and content relevance. Lower dependency on a single source. |

## Proof of Completion Process

If using Anthropic Academy courses, the following process applies:

Employee completes designated Academy course(s) and downloads their completion certificate

Employee submits certificate to the central tracker (HubSpot form, Google Sheet, or equivalent) with their name and level

Program lead reviews submission and marks the employee as certified in the tracker

Claude access is provisioned via SCIM only after the certification record is confirmed

## One Certification. One License.

All three modules are required. Completion of the full curriculum, passing the assessment, and signing the AUP results in one license granting full Claude access.

| Module | Content | Delivery |
| --- | --- | --- |
| Module 1 AI Fundamentals | How LLMs work. What AI can and can't do. Prompt basics. Setting expectations for AI-assisted work. | Anthropic Academy course + short quiz. |
| Module 2 Responsible Use at iAltA | Driving Zones in full (Zones 1, 2, 3, No-Drive). The AUP. Data classification. Real iAltA examples and edge cases. | Internal course + quiz. AUP signature required. |
| Module 3 Advanced Workflows | MCP servers: what they are, which are approved, why they auto-trigger Zone 3. Agentic task design. Jira-first enforcement. CLAUDE.md awareness. Zone 3 in practice. | Internal course + practical exercise. |

## Curriculum Build Tasks

Make the course strategy decision (Option A, B, or C above)

Audit the current Anthropic Academy catalog and designate specific courses for Module 1 (and Module 2 if applicable)

Build Module 2 internal course: iAltA Driving Zones, AUP walkthrough, data classification scenarios

Build Module 3 internal course: MCP servers, agentic workflows, Jira ticket process, hands-on exercise

Build assessments and quizzes for each module

Create the completion tracker and proof-of-completion intake process

Design the license record — a signed, dated completion document per employee

───────────────────────────────────────────────────────────────────────────────────────────────

PHASE 3  —  COMPANY-WIDE ROLLOUT

Once guardrails are live and the certification program is built, the program goes live for all employees simultaneously. Using AI without a license is a policy violation from day one.

All employees complete the full certification before Claude access is provisioned — no exceptions

SCIM-based provisioning configured and tested: access is tied to the certification record, no manual onboarding

Company-wide announcement via all-hands: program is now live, policy is in effect

Central certification tracker live and being maintained

───────────────────────────────────────────────────────────────────────────────────────────────

PHASE 4  —  STEADY STATE

The following annual touchpoints apply regardless of which ongoing engagement model is selected:

Annual re-certification — all employees re-read the AUP and re-sign

Annual vendor compliance review — obtain and review updated Anthropic SOC2 Type II report

Annual curriculum review — update course content for new Claude capabilities, policy changes, and new zones

Annual risk assessment update

Incident response drill — run a tabletop exercise with an AI-specific scenario

## Ongoing Engagement Model — CIO to Select

Choose one of the following models for how the program lead engages with employees on an ongoing basis:

## Option 1 — 1-on-1 Quarterly Usage Reviews

The program lead meets individually with each licensed employee once per quarter for a 1-hour session. Suggested structure:

15 min — Review actual usage from audit logs: tools used, zones invoked, frequency

20 min — Open Q&A: what's working, what's confusing, where they're avoiding AI because they're unsure of the rules

15 min — Coaching: suggest better workflows, correct Zone misclassifications, identify employees ready for more advanced use

10 min — Flag and log any policy edge cases for future curriculum updates

Best for: Surfacing real usage patterns and catching misuse early. Builds individual trust and adoption. Time cost scales linearly with headcount — plan accordingly.

## Option 2 — Weekly Office Hours

The program lead holds a standing 1-hour open session each week. No agenda, no required attendance — employees drop in with questions, use cases they're unsure about, or things they want to try but aren't sure are permitted. Pairs well with a shared Slack/Teams channel for async questions between sessions and a running FAQ log built from recurring questions.

Best for: Fast feedback loop during early adoption with minimal scheduling overhead. Requires consistent presence but no prep work.

## Option 3 — Monthly Mandatory Group Sessions

All employees attend a 1-hour monthly session. Suggested structure:

15 min — Usage recap: aggregate trends from audit logs (anonymized), common patterns, wins

20 min — Case study or demo: one real use case from the past month, instructive or cautionary

15 min — Policy/curriculum update: anything that changed, newly approved MCP servers, zone clarifications

10 min — Open Q&A

Best for: Keeping the whole company aligned and building a shared AI culture. Efficient as headcount grows. Less personalized than 1-on-1s — individual edge cases may stay hidden.

## Option 4 — Tiered Engagement by Usage Level

Match engagement intensity to how actively and riskily each employee uses Claude:

Light users — monthly group session only (low risk, broad audience)

Regular users — monthly group + quarterly 30-minute 1-on-1

Heavy / agentic users — monthly group + monthly 30-minute 1-on-1 + ad-hoc audit log reviews

Best for: Focusing program lead time where complexity and risk are highest while keeping everyone informed.

## Option 5 — Async-First with Periodic Escalation

The primary channel is a dedicated Slack/Teams channel monitored by the program lead. A monthly written digest covers top questions, notable usage patterns, policy reminders, and curriculum updates. Live sessions are reserved for policy incidents, major Claude capability changes, or annual re-certification.

Best for: Lean organizations where meeting overhead is a concern. Lower signal on adoption issues — problems may surface later than with other models.

───────────────────────────────────────────────────────────────────────────────────────────────

Recommendation: Option 4 (Tiered by Usage) balances program lead time against risk proportionality. Option 2 (Office Hours) pairs well with any choice as a low-cost safety valve during the first year.